## Work List
Milestone | Pri | Owner | Cost (days) | Progress | Remaining (days) | Area | Feature | Description | Notes
|  | JoshuaM | 1 | 100% | 64 | Game dev | Create the Project | Create the unity project, github, and work break down sheet
|  | J.M. & S | 2 | 100% | 62 | Unity | get the unity asset store unblocked | get an unban request from the school IT…
|  | JoshuaM | 4 | 100% | 58 | Paint.net | Sprites | create sprites such as the ties and the main charecter and background for game
|  | JoshuaM | 1 | 100% | 57 | Unity cloud | Collaberation | Figure out a way for us to wok on the same unity project through unity cloud so that we can both be productive at the same time
|  | JoshuaM | 3 | 100% | 54 | Unity | Scripts | Make Background loop for an array of game objects
|  | JoshuaM | 2 | 100% | 52 | Unity | Scripts | create a movement script for the player and the enemy
|  | JoshuaM | 5 | 100% | 47 | Unity | Scripts | create a paralax script for the player camera nd background (this was later not needed and overkill) D:
|  | JoshuaM | 2 | 100% | 42 | Unity | Scripts | Make a dammage script for the spikes and the enemys that could be added in to the game
|  | JoshuaM | 2 | 100% | 40 | Unity | Scripts | Make a health script so that the player can heal, take dammege, and have a game over screen if he dies.
|  | JoshuaM | 5 | 100% | 35 | Unity | UI | Create multiple scenes so that the player has a menu to navigate through before playing the game
|  | JoshuaM | 1 | 100% | 34 | Unity | UI | Figure out how buttons work and create a small script so that the player can use them to traverse scenes (This took me longer than I would like to admit...)
|  | JoshuaM | 6 | 100% | 28 | Unity | UI | Create the most annoying health interface for the player by representing how much health they have left with immages resulting in me spending an incredibly long time debugging the code than just starting over on a simpler UI
|  | JoshuaM | 1 | 100% | 27 | Unity | UI | Create multiple scenes so that the player has a menu to navigate through before playing the game
|  | StrummerL | 3 | 100% | 0 | paint.net | sprite and asset design | designed main character, ground/object textures
|  | JoshuaM | 3 | 100% | 24 | Unity | Level Design | Create gameplay and improve level design (obstacles, enemys, and anobjective) for level 1
|  | JoshuaM | 3 | 100% | 21 | Unity | Level Design | Create gameplay and improve level design (obstacles, enemys, and anobjective) for level 2
|  | JoshuaM | 3 | 100% | 18 | Unity | Level Design | Create gameplay and improve level design (obstacles, enemys, and anobjective) for level 3
|  | StrummerL | 3 | 100% | 0 | Unity | Level Design | Create gameplay and improve level design (obstacles, enemys, and anobjective) for level 4
|  | JoshuaM | 3 | 100% | 15 | Unity | Level Design | Create gameplay and improve level design (obstacles, enemys, and anobjective) for level 5
|  | JoshuaM | 3 | 100% | 12 | Unity | Prefabs and file management | Help create all the prefabs so that we can use the tilemap easier
|  | Jack N | 5 | 100% | 12 | Paint.net | Sprites | Create new and better sprites that are polished and make the background of the game look a lot better by removing the placeholder sprites
|  | Jack N | 5 | 100% | 7 | Unity | Prefabs and file management | Help create all the prefabs so that we can use the tilemap easier
|  | Jack N | 2 | 100% | 5 | Unity | UI | Help debug code like the problem where the background would not repeat on only level 3 for some reason
|  | J.N & J,M | 5 | 100% | 7 | Unity | Level Design | Redesign all of the Game object tiles in every level by removing the game objects and instead using the more efficient grid collider that can be used with the new sprites that Jack and Josh created this both made it loock better but make changes more efficient.
|  | JoshuaM | 1 | 100% | 6 | File management | Build the game for bata test | For some reason there was a error in the Auniversal pipeline that stoped the project form being built so I loocked in to it and there was a library that we imported in a few scripts that caused the error so we removed it and it worked. :)
|  | JoshuaM | 5 | 100% | 1 | Unity | Scripts | Create a functional level select by amking multiple scripts such ass collect coin, Scene loader, and button tint to ensure that the level select both loocks good and functions.
|  | StrummerL | 5 | 80% | 1 | Sound Design | Soundtrack | Create main menu and level music
|  | StrummerL | 1 | 100% | 0 | Paint.net | Sprites | Created main character, static enemy, flying enemy (depreciated)
|  | StrummerL | 7 | 100% | 0 | Unity | Scripts | Created movement script, enemy movement script, aerial attack script (depreciated), double jump (implemented?),
|  | StrummerL | 2 | 100% | 0 | Unity | Scene management | designed 2/5 of the 1.0 levels, testing levels
|  | StrummerL | 2 | 100% | 0 | Unity | Animations | Main chracter blinking animation
|  | StrummerL | 1 | 100% | 0 | Unity | Gameplay | Tune Keybinds and movement speeds/friction
|  | StrummerL | 4 | ongoing | 0 | Github | Create the Repo | create github repo, insert all critical project files, consider how to add whole builds, sorting, issue handling, perms and others
|  | StrummerL | 2 | 100% | 0 | Paint.net | Sprites | "sussy spaceman", original flying enemy, original backgrounds, (all depreciated)
|  | StrummerL | 5 | 100% | 0 | Unity | Gameplay | Tuned josh's insanely hard levels to an acceptable level of difficulty
[6 empty] | Deadline | Remaining (workdays) | Critical Path Buffer (workdays) | My Buffer (workdays)
|  | M1 Total | 21 | #DIV/0! |  | 2024-03-06 | 0 | 43 | -22
|  | M2 Total | 42 | #DIV/0! |  | 2024-04-04 | 0 | 22 | -22
|  | M3 Total | 63 | #DIV/0! |  | 2024-06-06 | 0 | 1 | 1
|  | Total dev days: | 64 | #DIV/0! | 0

## Pivot Table
Sum of Remaining (days) | Owner
Milestone | TBD | ChadM | Grand Total
(blank) | 10 | 30.75 | 40.75
Grand Total | 10 | 30.75 | 40.75